# Project Activity Log

Clayton Thomas McIntyre
January 15, 2025

# Triton Envelope Issue

No Update, still need to order posts. Priority has been weld development for GNF3, but we should probably order the oversized posts this next week

# Welder 2/GNF3 Qualification

Thank you to everyone for your patience!

5 spacers have been submitted to Metlab and cross sectioned so far, we have a good handle on all weld types except for the tab welds

Back reflection errors have been a major pain point on both welders; we’ve had to introduce tilt to the tab welds to avoid reflection errors on welder 2 and will likely have to do so for 6, introducing a tilt is not trivial

Currently, we’re exclusively using non-scrap inventory as I need to rule out bad parts as a cause for any issues encountered, we need to keep an eye on inventory levels to ensure we have what is needed for when production starts

Fixture is currently in the process of being modified, I’m continuing tab weld development on the upper fixture

Laser perimeters are not updating reliably, meaning they need to be set manually which slows us down

Our optimizer software is currently not functioning properly

Harry was out sick over the holidays, bug list has been growing and he’s only been able to start working on things again this week

What I believe is the final weld development spacer was submitted on Tuesday, once those results are back we will establish minimum and maximum settings for each weld type

Depending on the results, met lab may need to do more cross sectioning on the spacer I turned in which will take another day or so

Tentative Timeline for GNF3 Qualification:

Phase 1 Automation: weld one spacer at nominal for QA buy off, set to begin between 1/14/2026-1/16/2026

Phase 1 QA: Results for phase 1 by 1/21/2026

Phase 2A Automation: 5 Samples of each weld type at high, low, nominal submitted to metlab 1/23/2026

Phase 2A QA: Results by 1/28/2026

Phase 2B Automation: (Can this be done concurrently with phase 2A?) Submit Nominal Spacer to QA 1/28/2026

Phase 2B QA: Full inspection, heat treat etc. of submitted nominal spacer 2/2/2026

Phase 3 Automation/Production: Weld 35 Spacers Week of 2/2/2026

Phase 3 QA/Production: Finishing inspection, heat treat, final inspection, packaging, shipping etc. Week of 2/9/2026

Note on timeline: This timeline is for qualifying the lowers only, however we’re going to attempt to qualify uppers and lowers simultaneously, because I think I can extrapolate minimum/maximum settings for the upper unique weld types from the knowledge I’ve gained from weld development. We still need to modify the upper fixture which will delay things a bit, and add 1-2 weeks to this timeline, also it’s possible my extrapolations are wrong in which case we will finish qualifying lowers and then proceed to uppers.

# Welder 6

Assisted Eric when needed

# Triton Overlay

Have the necessary modifications been made to the die?

When are the A cells running?

Is everything in place for validation of the parts?

Is anything further needed from automation?

Configured fixtures for Jose to test assemble spacers, if he is happy with how they assemble then that’s a green light to finish the A cells

# Miscellaneous

Assisted with 3D Printing