# Project Activity Log

Clayton Thomas McIntyre
January 29, 2025

# Triton Envelope Issue

Luis Delgado thinks it will be cheaper and faster if we outsource the work because the posts take a lot of time

Luis is getting estimates for outsourcing the work, once I get an estimate from him we will need to decide if we will make in house or outsource

TE# for posts is approved

Posts are being ordered from outside vendor

Request to order posts sent to Lazaro

# Welder 2/GNF3 Qualification

QA determined the waves on the bands, particularly around the double dividers are unacceptable

Evan and I have been troubleshooting the issue, we’ve made some headway adjusting the setscrews and clamping force on the pushers

Adjustments on the pushers have caused other issues to arise, such as rollback on the seams and blowing holes in tabs, these issues will need to be addressed once we’ve solved the waviness, solving the emergent issues should be much easier than the waviness problem

After numerous tests, we have determined that the only way we can reliably produce spacers without waviness is by not fully seating the parts, which allows the dividers and bands to “float”

A modification is being made to the fixture, bringing down the surface the bands sit on down by 0.005” to allow only the bands to “float”

If bringing down that surface does not work, we will need to decide if we want to lower it more, or possibly make a modification to the top plate to allow the dividers to also “float”

We have encountered issues with blowing holes in tab welds, the reason the holes appear is the band not fully seating, allowing a gap between the divider and the band (see picture at end of report)

I don’t think we can lengthen the dividers because the gap is not consistent on all sides, and making them longer could negatively impact other sides

We’re going to try to increase clamp force on the pushers to resolve the issue, provided our fixture modification fixes the waviness issue we should be able to significantly increase clamping force

I’ve put together a new schedule for qualification, see next page

# Power Meter Test

Last week I Set up welder 2 power meter with beam expander, forgot to put it in report

Began taking and recording daily power readings to see how readings change over time

- GNF3 Qualification Timeline

- Blue Text is Lower Qualification

- Black Text is Upper Qualification

- Lower Fixture returned from NTR: 2/2/2026

- Phase 1, Automation, Lower: weld one spacer at nominal for QA buy off 2/2/2026

- Phase 1, QA, Lower: Results for phase 1 by 2/4/2026

- Assuming fixture modification to Lower works, submit Upper fixture for modification on 2/4/2026

- Phase 2A, Automation, Lower: 5 Samples of each weld type at high, low, nominal submitted to metlab 2/6/2026

- Upper Fixture returned from NTR 2/9/2026

- Phase 1, Automation, Upper: weld one spacer at nominal for QA buy off 2/9/2026

- Phase 2A, QA, Lower: Results by 2/9/2026

- Phase 2B, Automation, Lower: Submit Nominal Spacer to QA for heat treat (Oven available all week) 2/9/2026

- Phase 1, QA, Upper: Results for phase 1 by 2/11/2026

- Phase 2A, Automation, Upper: 5 samples of each weld type at high, low, nominal submitted to metlab 2/12/2026

- Phase 2B, QA, Upper: Full inspection, heat treat of submitted nominal spacer 2/12/2026

- Phase 2A, QA, Upper: Results by 2/16/2026

- Phase 3 Automation/Production, Lower: Weld 35 Spacers Week of 2/16/2026

- Phase 3 QA/Production, Lower: Finishing inspection, heat treat, final inspection, packaging, shipping etc. Week of 2/23/2026

- Phase 3 Automation/Production, Lower: Weld 35 Spacers Week of 2/23/2026

- Phase 3 QA/Production, Lower: Finishing inspection, heat treat, final inspection, packaging, shipping etc. Week of 3/2/2026